## Material Submittals Schedule
SCHEDULE OF MATERIAL SUBMITTALS | [16 empty] | PROJECT NAME & NKAK # - NKAK 201032 Repair (SUS) Replace Natural Gas Components |  |  |  | Solicitation
(To be completed by Project Engineer) | [14 empty] | (To be completed by Contract Administrator)
NUMBER OF COPIES REQUIRED
LINE NUMBER | ITEM OR DESCRIPTION OF ITEM, CONTRACT REFERENCE, TYPE OF SUBMITTAL | CERTIFICATION OF COMPLIANCE | SHOP DRAWINGS | SAMPLES | COLOR SELECTION | MANUFACTURER'S RECOMMENDATION | MANUFACTURER'S WARRANTY | CATALOG DATA | OPERATING INSTRUCTIONS | SCHEDULES, LISTINGS, REPORTS, PLANS | TECHNICAL DATA | TEST REPORTS | FIELD REPORTS | REQUIRED SUBMISSION DATE | DATE RECEIVED IN CONTRACTING | DATE TO CIVIL ENGINEERING | RETURN SUSPENSE DATE | SUBMITTAL NUMBERS | DATE CONTRACTOR NOTIFIED |  | CONTRACTOR RESUBMITTAL | FINAL APPROVAL | REMARKS
[19 empty] | APPROVED | DISAPPROVED
| 03 00 00 Cast-In-Place Concrete |  | X |  |  |  |  | X
| 09 91 00 Painting | X | [5 empty] | X |  |  | X
| 22 16 10 Fuel Piping | X | [5 empty] | X |  |  |  |  | X
| 26 05 19 Building Wire and Cable |  |  |  |  | X |  | X
| 26 05 25 Conduit | [6 empty] | X
Note on O6: Enter the due date from the Contractor (MM/DD/YY)
Note on P6: Enter the date received from the Contractor. (MM/DD/YY)
Note on Q6: Enter the date submittal was given to CE for review. (MM/DD/YY)
Note on R6: Enter the date the submittal is due back from CE (MM/DD/YY)
Note on S6: Enter the Submittal Number
Note on V6: Enter Resubmittal Number
Note on W6: Enter the submittal final approval date (MM/DD/YY)
Note on X6: Enter any comments pertaining to the submittal
Note on T7: Enter date the Contractor was notified of submittal approval (MM/DD/YY)
Note on U7: Enter date the Contractor was notified of submittal disapproval (MM/DD/YY)